# Project Plan

Project title: Collaborative robotic coffee serving system
Team members: Mullainathan, David, Safwan, Maritza Elizabeth

## 1. Project Background

This project focuses on the development of an automated coffee-serving system using two Universal Robots UR10 collaborative robots. The system is intended to demonstrate how multiple robots, vision-based object detection, human-machine interaction, and supervisory control can be integrated into a coordinated automation task.

The system will allow a user to place a coffee order through an operator interface, while the robotic system identifies and handles the required objects, such as a cup and beverage containers. One robot will primarily handle the cup, while the second robot will handle the beverage and perform the serving operation.

The project is motivated by the need to integrate perception, robot manipulation, communication, and user interaction into one practical robotic application, while maintaining a realistic and scalable scope for the available time and resources.

## 2. Project Goal and Objectives

Project Goal

The goal of the project is to develop a functional automated coffee-serving system integrating robot manipulation, vision-based object identification, and user interaction to complete a coffee-serving sequence.

Main Objectives

- Investigate and familiarize with the available UR10 robots, grippers, vision, and communication technologies, and determine their suitability for the coffee-serving system.

- Develop the system’s components which include but not limited to robot operations, object identification, communication, and user interface required to complete the coffee-serving sequence.

- Integrate the developed components into a functional coffee-serving system.

- Test the individual components and the integrated system, evaluating their functionality and performance.

- Document the system development, implementation, testing, and evaluation of results.

## 3. Scope and Limitations

Define what is included (in scope) and not included (out of scope) in the project.

The scope should be realistic considering the available time, resources, and competencies of the team.

In Scope

- One UR10 and one UR10e robot with their native controllers and PolyScope programs.

- Coffee serving using a predefined cup and coffee as the main beverage.

- A web-based customer and operator HMI.

- A Python-based supervisory controller and state machine.

- Camera-based identification of the cup and relevant objects within a defined workspace.

- Predefined object positions and robot operations for the initial implementation.

- Investigation of the possibility of adding conveyor control.

- Ethernet and/or digital I/O communication between system components.

- Suitable grippers or minor gripper adaptations.

- Fault messages, timeouts, process logging, and basic recovery.

- Repeated testing of the integrated demonstrator.

Out of Scope

- Support for tea, juice, water, or other beverages.

- Support for arbitrary objects or uncontrolled environments.

- Fully dynamic robot motion planning or continuous trajectory streaming.

- External control of individual robot joints.

- ROS 2 as a required part of the system.

- Commercial payment or user-account functionality.

- Certification as a production-ready food-service system.

- High-speed simultaneous robot operation in a shared workspace.

## 4. Requirements and Success Criteria

Define the most important requirements for the project and how you will determine whether they have been fulfilled.

| ID | Requirement | Priority | How will it be verified? |
| --- | --- | --- | --- |
| R1 | The system shall use the existing UR10 and UR10e robots to perform the coffee-serving task. | Must | Functional test confirming that both robots perform their assigned operations. |
| R2 | A user shall be able to place a coffee order through the HMI, which shall provide basic information about the order status. | Must | Functional test of order submission and status display. |
| R3 | The system shall identify the predefined cup and coffee container using vision before manipulation. | Must | Repeated tests with the predefined objects. |
| R4 | The robots shall safely handle the cup and coffee container and coordinate their operations during the serving process. | Must | Repeated serving tests, recording handling and coordination failures. |
| R5 | The system shall complete the defined coffee-serving sequence and deliver the filled cup to a predefined serving position. | Must | Repeated end-to-end tests measuring successful sequence completion. |
| R6 | The system should provide reliable communication between the robots and the required system components. | Should | Monitor communication during repeated serving cycles and record communication failures. |
| R7 | The system could support different cup sizes and allow the user to customize the coffee by adding milk. | Could | Test the defined options through the HMI and verify the corresponding serving operation. |
| R8 | The feasibility of integrating conveyor control for supplying the cup should be investigated. | Could | Investigation and, if feasible, a basic integration test. |

## 5. Technical Approach

A central PC will run a Python-based supervisory controller connected to a web HMI developed using HTML, CSS, and JavaScript. The supervisor will manage the process sequence, send high-level commands, monitor subsystem status, handle faults, and update the HMI.

Robot movements will be programmed locally in PolyScope. The supervisor will send commands such as PICK_MUG, POUR_COFFEE, POUR_MILK, DELIVER, and HOME, while the robots return READY, BUSY, DONE, or FAULT.

For black coffee, one robot will hold the mug while the other handles and pours from the coffee kettle. Milk pouring will be added later as an optional extension. A Python/OpenCV vision system will verify the mug, objects, and pouring area.

Communication will initially be tested using digital I/O, followed by Ethernet if supported by both controllers. The baseline will use a fixed mug pickup station, while a conveyor will be investigated as an optional addition.

## 6. Work Packages and Responsibilities

Divide the project into major activities or work packages.

| Work package / activity | Description | Responsible person(s) | Expected result |
| --- | --- | --- | --- |
| WP1 Robot programming and coordination | Layout, frames, PolyScope routines, grippers, zones, and robot tests | David (Lead) | Tested task programs and coordinated sequence |
| WP2 Vision and perception | Camera setup, image collection, cup and workspace verification, accuracy testing | Maritza (Lead) | Vision module providing reliable verification |
| WP3 HMI and supervisory controller | Interfaces, state machine, communication, logging, and faults | Mullai (Lead), Safwan | Application coordinating the complete process |
| WP4 – Mechanical Setup and Hardware Adaptations | Physical solutions required to support robotic tasks, including mug supply and positioning, gripper adaptations, and possible conveyor integration. | Safwan (Lead) | Suitable physical setups and hardware adaptations to support reliable robot operation, with a defined approach for mug supply and an assessment of conveyor integration. |
| WP5 Integration and evaluation | Interface integration, safety checks, end-to-end testing, and KPIs | All members | A functional integrated coffee-serving demonstrator and documented test results. |

Responsibilities may change during the project, but everyone in the team should have a clear role and contribute to the technical work.

## 7. Project Schedule and Milestones

Create an overall plan for the project.

Identify the most important milestones and expected dates.

| Milestone | Target date | Expected outcome |
| --- | --- | --- |
| M1: Investigation and technology assessment | 24.09.2026 | Relevant technologies and suitable approaches identified. |
| M2: Finishing individual WP1-4 | 18.10.2026 | Main components developed and tested. |
| M3: Mid Term Presentation | 20.10.2026 | Project progress presented and evaluated. |
| M4: Integration of the system and assembly | 06.11.2026 | Main components integrated into one system. |
| M6: Practical Presentation | 03.12.2026 | Integrated system demonstrated. |
| M7: Adjustments and improvements | 11.12.2026 | Identified issues addressed and system improved. |
| M8: Future plan and documentation | 31.12.2026 | Project results documented and future work identified. |
| M9: Final presentation | TBD | Final project presented. |

## 8. Testing and Evaluation Plan

Describe how you intend to test and evaluate your solution.

| Area | Test method | Success criterion |
| --- | --- | --- |
| Robot operation | Repeat local robot tasks in dry operation | 20 successful repetitions without an unhandled failure |
| Vision and mug handling | Repeatedly identify, pick up, and handle predefined objects | At least 18 successful trials in 20 attempts |
| HMI and communication | Submit orders, monitor status, and repeat command/acknowledgement tests | Orders and communication operate correctly, with safe timeout handling |
| Robot coordination | Monitor shared-zone use during repeated operations | No unauthorized simultaneous zone entry or unsafe interaction |
| Black-coffee system | Repeat complete order-to-delivery trials | At least 18 successful runs in 20 trials |
| System performance | Record order-acceptance and order-ready times | Average and variation in cycle time are reported |
| Optional features | Test milk sequence or conveyor if implemented | Evaluated after the baseline coffee system is successful |

## 9. Risks and Mitigation

Identify the most important risks that could affect the project.

| Risk | Probability | Impact | Mitigation or Plan B |
| --- | --- | --- | --- |
| Communication differences between robots | Medium | High | Check controller versions early and use a commonly supported interface, with digital I/O as fallback. |
| Collision in the shared workspace | Medium | High | Minimize workspace overlap and use safe poses, zone interlocks, reduced speed, and dry testing. |
| Gripper or object-handling problems | High | High | Test objects early, adapt the grippers, or use a simpler fixed dispenser. |
| Vision affected by lighting or object position | High | Medium | Control lighting and use fixed camera and predefined object positions. |
| Integration takes longer than expected | High | High | Define interfaces early, integrate regularly, and remove optional features first. |
| Limited laboratory access or unsafe liquid handling | Medium | High | Reserve lab time and begin with dry tests or room-temperature water. Use a dry demonstration if liquid operation is not approved. |

## 10. Resources and Support Needed

Highlight resources that are critical for starting or completing the project.

- UR10 and UR10e robots, controllers, pendants, and documentation.

- Grippers and coffee-serving equipment, including cups and coffee pot/dispenser.

- 3D printer and materials, if needed, for gripper attachments and fixtures.

- Camera and vision setup, including mounting and lighting.

- PC and network equipment, including Ethernet, cables, and power supplies.

- Fixed mug station and optional conveyor equipment for mug handling and feasibility testing.

- Software and project support, including Python, OpenCV, PolyScope, Git, and technical support for networking, electrical connections, and safety.

## 11. Team Organization and Ways of Working

The team will meet at least once a week at ASSAR for planning, technical development, and system integration. Additional meetings will be arranged, when necessary, particularly before major milestones.

Each member will lead one work package and be supported by a second member. However, responsibilities will not be limited to these assigned roles; all members are expected to contribute to integration, testing, safety reviews, documentation, and the final demonstration.

Project hours will be recorded in a shared calendar. Tasks, progress, important decisions, interface changes, meeting outcomes, and test results will be documented in OneDrive. Milestone and progress meetings will be used to review completed work, address problems, and plan the next activities.

The team will use:

- GitHub: Source code and version control

- OneDrive: Files, documentation, task management, meeting notes, and timesheets

- WhatsApp: Day-to-day communication and coordination

- Email: Formal communication with supervisors and external contacts

Knowledge will be shared through regular progress meetings, short technical demonstrations, peer reviews, shared documentation, integration stage and cross-participation between work packages.

## 12. Immediate Next Steps

List the most important actions for the next 2–3 weeks.

| Action | Responsible | Deadline |
| --- | --- | --- |
| Meet the supervisor to confirm scope, safety, and access. | All members | Week 0 |
| Review the plan and confirm module responsibilities | All members | Week 0 |
| Record robot controller models, PolyScope versions, network options, and available I/O | WP1 | Week 1 |
| Inspect and measure the cell, fixed mug station, available conveyor, camera, grippers, and objects | WP1 and WP4 | Week 1 |
| Create the shared repository, Kanban board, and test templates | WP3 with all members | Week 1 |
| Define the initial state sequence and subsystem interfaces | All members | End of Week 1 |
| Test robot reachability and identify the preliminary shared operating zone | WP1 | Week 2 |
| Demonstrate communication between the supervisory PC and both robots | WP1 and WP3 | Week 2 |
| Create an HMI prototype with simulated process progress | WP3 | Week 2 |
| Capture sample images and test mug detection and verification | WP2 | Week 2 |
| Build or identify a fixed mug pickup station and test presence detection | WP4 | Week 2 |
| Evaluate conveyor availability, positioning accuracy, control requirements, and integration effort | WP4 | Weeks 2–3 |
| Update the project plan using the feasibility-test results | All members | End of Week 3 |

These actions should be concrete enough that the team can start working immediately after the project plan is submitted.